## agri-tech project
Agri-Tech Project
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
To-Do
Name | Owner | Status | Due date | Priority | Notes | Files | Timeline - Start | Timeline - End | Last updated | Item ID (auto generated)
Research, Planning & Dataset | Profusion Communications | Working on it | 2024-10-15 | Low | Action items | https://profusioncs-team.monday.com/protected_static/26000734/resources/74220937/file.png | 2024-10-14 | 2024-10-15 | Profusion Communications Oct 16, 2024 3:16 AM | 1667222071
Annotation & Python Scripting |  | Done | 2024-10-17 | High | Meeting notes |  | 2024-10-15 | 2024-10-17 | Profusion Communications Oct 16, 2024 3:35 AM | 1667222069
Documenting and Reporting |  | Stuck | 2024-10-18 | High | Other |  | 2024-10-17 | 2024-10-18 | Profusion Communications Oct 16, 2024 3:35 AM | 1667222070
|  |  | 2024-10-15 to 2024-10-18 |  |  |  | 2024-10-14 | 2024-10-18
Completed
Name | Owner | Status | Due date | Priority | Notes | Files | Timeline - Start | Timeline - End | Last updated | Item ID (auto generated)
Research and Information Finding | kefilwephaahla190@gmail.com, Matomeseshoka97@gmail.com | Done | 2024-10-15 | Critical ⚠️️ |  |  |  |  | Profusion Communications Oct 16, 2024 3:40 AM | 1667223110
Annotation tool Research | Matimu Nghonyama, Profusion Communications | Done | 2024-10-15 | Critical ⚠️️ |  |  |  |  | Profusion Communications Oct 17, 2024 9:25 AM | 1667223231
Picture Collection | Nico, Earl Tlhagane earltlhagane29@gmail.com, Matimu Nghonyama | Done | 2024-10-15 | Critical ⚠️️ |  | https://profusioncs-team.monday.com/protected_static/26000734/resources/74453719/raw_ann_picture.zip |  |  | Profusion Communications Oct 17, 2024 9:25 AM | 1667223295
Picture Annotation | Nico, Bruce | Done | 2024-10-17 | High |  | https://profusioncs-team.monday.com/protected_static/26000734/resources/74332666/Grapevine_Annotated_Dataset.zip | 2024-10-15 | 2024-10-17 | Profusion Communications Oct 17, 2024 9:56 AM | 1667223416
Dataset Cleaning | Profusion Communications | Done | 2024-10-17 | Medium |  | https://profusioncs-team.monday.com/protected_static/26000734/resources/74449946/Complete_Dataset%20-%20Merged_Dataset.csv.csv, https://profusioncs-team.monday.com/protected_static/26000734/resources/74452458/Merge_Complete_Dataset.py, https://profusioncs-team.monday.com/protected_static/26000734/resources/74452461/All_Images_InOne4CVAT.py, https://profusioncs-team.monday.com/protected_static/26000734/resources/74452459/Splitting%20the%20data%20to%20organize.py | 2024-10-16 | 2024-10-17 | Profusion Communications Oct 17, 2024 9:56 AM | 1667223485
Python Scripting | Matimu Nghonyama, Profusion Communications, Matomeseshoka97@gmail.com, Earl Tlhagane earltlhagane29@gmail.com, Bruce, Nico, kefilwephaahla190@gmail.com | Done | 2024-10-17 | High |  | https://profusioncs-team.monday.com/protected_static/26000734/resources/74458602/Exploratory%20Data%20Analysis.pdf, https://profusioncs-team.monday.com/protected_static/26000734/resources/74461200/Organised_Ann_Pictures.zip | 2024-10-15 | 2024-10-17 | Profusion Communications Oct 17, 2024 9:56 AM | 1667223534
Presentation | Matomeseshoka97@gmail.com, kefilwephaahla190@gmail.com | Working on it | 2024-10-18 | Medium |  |  | 2024-10-17 | 2024-10-18 | Profusion Communications Oct 16, 2024 3:41 AM | 1667223618
Report | Profusion Communications, Earl Tlhagane earltlhagane29@gmail.com, Matomeseshoka97@gmail.com, Nico, kefilwephaahla190@gmail.com, Bruce, Matimu Nghonyama | Done | 2024-10-18 | High |  |  | 2024-10-17 | 2024-10-18 | Profusion Communications Oct 18, 2024 2:31 AM | 1667223632
|  |  | 2024-10-15 to 2024-10-18 |  |  |  | 2024-10-15 | 2024-10-18

## agri-tech project-updates
Agri-Tech Project | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
1667222071 | Research, Planning & Dataset | Update |  | Profusion Communications | 16/October/2024 03:20:20 AM | Research, Planning and Dataset Collect 100 + Pictures For Annotation Information Research and Findings Annotation Tools | 0 |  | 337198373